## TBPQC_2026_100_Point_Quality_Sh
Project Name:
Site Number:
Engineer:
Section | Check ID | Description | Status
1. Pre-Construction & Engineering Drawings | 1.01 | Verification of Project Work Schedule and timeline alignment.
| 1.02 | Availability of approved Floor Plans and Architectural drawings at site.
| 1.03 | Verification of Center Line diagrams for column footings.
| 1.04 | Review of Excavation and Sump tank diagrams.
| 1.05 | Check of Column Footing reinforcement detail drawings.
| 1.06 | Availability of Plinth Beam structural drawings.
| 1.07 | Review of Column reinforcement and Lap detail drawings.
| 1.08 | Verification of Roof Shuttering and Leveling layouts.
| 1.09 | Review of Roof Beam and Slab reinforcement detail drawings.
| 1.1 | Verification of MEP (Mechanical, Electrical, Plumbing) shop drawings.
2. Material Quality & Testing Standards | 2.01 | Reinforcement steel verification as per contract specifications (Brand & Grade).
| 2.02 | Cement verification (OPC 53 for RCC, PPC for Masonry as per specs).
| 2.03 | On-site Silt Test and organic matter check for M-Sand/River Sand.
| 2.04 | Field tests for Concrete Blocks (Dimensional accuracy & Water absorption).
| 2.05 | Cement field tests (Lump check, Fineness, and Setting time observation).
| 2.06 | Verification of Coarse Aggregate size and cleanliness.
| 2.07 | On-site Slump Test for every concrete batch to ensure workability.
| 2.08 | Casting of Concrete Cubes for 7-day and 28-day compressive strength testing.
| 2.09 | Storage inspection: Cement bags kept in moisture-free, raised platforms.
| 2.1 | Verification of Branding and Quality for all MEP conduits and pipes.
3. Earthwork, Foundation & Sub-structure | 3.01 | Excavation pit depth and width verification against finished ground level.
| 3.02 | Checking for loose soil and ensuring adequate shoring/timbering in pits.
| 3.03 | PCC Surface preparation and marking levels with respect to drawing.
| 3.04 | Verification of PCC thickness and ensuring no extra cement mortar on top.
| 3.05 | Curing of PCC for a minimum of 7 days.
| 3.06 | Anti-termite treatment: Soil preparation and chemical mix proportion (Manufacturer's instructions).
| 3.07 | Anti-termite application: Uniform spray on horizontal and vertical surfaces.
| 3.08 | UG Sump: Rough plastering outside and smooth plastering inside with mesh to avoid cracks.
| 3.09 | UG Sump: Corner rounding on the inside and checking for water-tightness.
| 3.1 | Bitumen Membrane coating for foundation protection against sub-soil moisture.
4. Structural Reinforcement & Formwork | 4.01 | Verification of Center line and Offsets for footings and columns.
| 4.02 | Footing reinforcement: Check for bar diameter, spacing, and 'L' bends.
| 4.03 | Column reinforcement: Check for main bars, stirrups spacing, and master rings.
| 4.04 | Provision of 50mm clear cover for footings and 40mm for columns.
| 4.05 | Check for column verticality (Plumb) before and during concreting.
| 4.06 | Formwork: Check for stability, leak-proof joints, and application of shuttering oil.
| 4.07 | Plinth Beam reinforcement and stirrups positioning as per structural design.
| 4.08 | Leveling of Plinth Beams and checking for Top of Concrete (TOC) levels.
| 4.09 | Special confining reinforcement at column-footing junctions (min 300mm extension).
| 4.1 | Damp Proof Course (DPC) application at plinth level.
5. Concrete Quality & Casting | 5.01 | Verification of Concrete Mix design/ratio (M20, M25 etc.) as per structure.
| 5.02 | Compaction: Use of mechanical vibrators for all RCC elements to eliminate honeycombing.
| 5.03 | Roof Shuttering: Inspection of props, spacing, and bracing for stability.
| 5.04 | Roof Reinforcement: Checking main bars, distribution bars, and chair supports.
| 5.05 | Slab thickness verification during casting using leveling markers.
| 5.06 | Staircase reinforcement and shuttering as per architectural flight/tread details.
| 5.07 | Curing: Continuous ponding/wetting for 14 days minimum for slabs.
| 5.08 | De-shuttering timeline adherence (Slab - 14 to 21 days based on span).
| 5.09 | Checking for honeycombing after formwork removal and immediate rectification.
| 5.1 | Expansion joints verification in large structural sections if applicable.
6. Masonry, Wall Construction & Plastering | 6.01 | Brickwork: Checking for soaking of bricks/blocks before use.
| 6.02 | Wall Alignment: Checking for plumb and straightness of every course.
| 6.03 | Mortar Mix: Checking for proper ratio and consistency of cement-sand mix.
| 6.04 | Structural Integrity: Mandatory GI/Fiber mesh at all RCC-to-brick junctions.
| 6.05 | High-density Hacking (50+ per sq. ft.) on concrete surfaces before plastering.
| 6.06 | Internal Plastering: Checking for thickness and smooth finish.
| 6.07 | 12mm Shadow-Gap (U-Groove) detailing at skirting and ceiling junctions.
| 6.08 | External Plastering: Checking for water-repellent additives and line-level.
| 6.09 | Curing of Masonry and Plastering for 7 to 10 days.
| 6.1 | Anti-Efflorescence treatment for masonry walls to prevent salt patches.
7. Waterproofing & Anti-Dampness Systems | 7.01 | Sunken Slabs: 4-layer Crystalline waterproofing system application.
| 7.02 | Mandatory Water Ponding test for 48 hours for all wet areas.
| 7.03 | Double-Slope Logic: Sloping the structural slab and tile level to avoid stagnation.
| 7.04 | External Walls & Sajjas: Specialized waterproofing and drip-edge details.
| 7.05 | Check for plumbing pipe sleeves/pockets to be properly grouted.
| 7.06 | Terrace Waterproofing: Checking for screed slope and thermal insulation.
| 7.07 | Basement/Ground Floor: M25 Grade Structural slab to prevent moisture rise.
| 7.08 | Epoxy Grout: Checking for usage in all wet area tile joints.
| 7.09 | Window sill & Door frame junction sealing to prevent seepage.
| 7.1 | Overhead Tank: Food-grade epoxy coating and water-tightness test.
8. MEP - Advanced Plumbing & Drainage | 8.01 | Verification of Astral CPVC Pro or equivalent brand pipes and fittings.
| 8.02 | Manifold Hub System: Checking for centralized water distribution units.
| 8.03 | Loop Piping: Ensuring constant water pressure across all outlets.
| 8.04 | Hydro-testing of all internal plumbing lines at 5-7 kg/cm2 pressure.
| 8.05 | Checking for proper pipe clamping and support spacing.
| 8.06 | Waste water lines: Verification of slope and provision of clean-outs.
| 8.07 | Sewerage: Multi-stage inspection of manholes and chamber connectivity.
| 8.08 | Sanitary fixtures: Budget and brand verification (Jaguar/Kohler range).
| 8.09 | Checking for CP fixture height and alignment as per user convenience.
| 8.1 | Solar Water Heater line routing and insulation check.
9. MEP - Electrical, Automation & EV Infrastructure | 9.01 | Verification of Anchor/Panasonic FR-LSH wiring and HMS conduits.
| 9.02 | Electrical Conduit Layout: Checking for depth and horizontal/vertical runs.
| 9.03 | Automation Backbone: Pre-laying 'dead pipes' for future smart sensors and CAT6.
| 9.04 | EV-Ready: Installation of industrial-grade conduits for 22kW chargers.
| 9.05 | 3-Phase electrical system: Dedicated circuits for high-capacity appliances.
| 9.06 | Distribution Board (DB): Proper labeling and use of MCBs/ELCBs.
| 9.07 | Earthing: Checking for proper earth pit and resistance value testing.
| 9.08 | Switch/Socket position: Verification against furniture and architectural plan.
| 9.09 | Back-up Power: Conduit routing for UPS/Inverter or Generator integration.
| 9.1 | Site Governance: Functionality check of 4K monitoring cameras.
10. Architectural Finishes & Quality Audit | 10.01 | Flooring: 4x6 ft Large Format Vitrified Slabs layout and leveling.
| 10.02 | Vibration-Based Leveling for tiles to ensure 100% adhesive coverage.
| 10.03 | Hollow Sound Check: Tapping tiles to ensure no voids/air pockets.
| 10.04 | Painting: Surface preparation (Putty, Sanding, Primer) before final coat.
| 10.05 | Verification of Asian Paints Royal Luxury Emulsion (Internal) & Apex Ultima (External).
| 10.06 | Doors & Windows: Checking for frame stability, alignment, and hardware.
| 10.07 | External Fencing: High-end WPC Slats installation and finishing.
| 10.08 | Final Site Cleaning: Removal of debris and thorough post-construction cleanup.
| 10.09 | Snag List: Final walkthrough to identify and fix minor defects.
| 10.1 | Documentation: Handover of 'As-Built' drawings and material warranty certificates.